Request for Proposal (RFP)

For: 	Qualitative Research for the Online Teacher Community (OTC) within Future English programme

Date: 	 31 January 2022

1	Overview of the British Council

1.1 	The British Council is the UK’s international organisation for cultural relations and educational opportunities. We create friendly knowledge and understanding between the people of the UK and other countries. We do this by making a positive contribution to the UK and the countries we work with – changing lives by creating opportunities, building connections and engendering trust.

1.2	We work with over 100 countries across the world in the fields of arts and culture, English language, education and civil society. Each year we reach over 20 million people face-to-face and more than 500 million people online, via broadcasts and publications. Founded in 1934, we are a UK charity governed by Royal Charter and a UK public body

1.3 	The British Council employs over 10,500 staff worldwide. It has its headquarters in the UK, with offices in London, Manchester, Belfast, Cardiff and Edinburgh. Further information can be viewed at www.britishcouncil.org.

2	Introduction and Background to the Project / Programme

Future English is a multiyear, multi-country programme, designed and delivered by the British Council. It aims at providing ministries and stakeholders with high quality research and consultancy into English language learning and teaching, enabling them to make informed decisions about the future of education in six countries of South Caucuses, Kazakhstan, Ukraine, and Uzbekistan.

The programme also uses research to provide ministries and teachers with Continuing Professional Development opportunities that best meet their needs, enabling teachers across the region to grow as practitioners and professionals. This objective is being fulfilled by offering the English language teachers in these countries an online ongoing professional development programme using an innovative Online Teacher Community platform.

2.1 	Context

Young people have a role to play in economic life and in community development, and this role is enhanced by access to the English language. According to English Effect (the British Council’s 2013 publication), research shows how a good command of English can not only enhance an individual’s economic prospects but also contribute to national growth and competitiveness. As well as employment opportunities, English is becoming increasingly important for further and higher education and for accessing courses in other countries and also self-access digital courses.

In six countries in which Future English is being delivered there are still significant challenges in education for young people, including those from remote/rural/edge of conflict areas. Girls in particular often have limited access to skills and learning opportunities in parts of the region (FCO Girls’ Education 2018) and this, together with other barriers in society, continues to limit their future employability and their capacity to influence or to engage the development of their communities and peacebuilding. English teachers are often poorly trained, are still using outdated and ineffective methodologies, and have few opportunities for continuing professional development. Schools often lack support and study materials (including multimedia) further limiting opportunities for learning. Students therefore have limited chances for better careers and better lives, the impact of which is particularly negative in isolated and rural communities and in communities populated by marginalised groups such as ethnic minorities and IDPs.

2.2 	The problem being addressed by the programme

English is a vital 21st Century skill for 140m people in Wider Europe under the age of 24.  For a previous generation in this region, Russian was considered the language of opportunity. Education systems have been slow to respond to the need for English with inadequate training for English teachers across the region and outdated methodology and teaching and learning resources resulting in poor quality teaching and low levels of English among school-leavers. In particular, young people do not have the English skills to engage effectively in English medium higher education or a wide range of employment opportunities. Limited English therefore reduces their prospects of employment, access to international opportunities and different worldviews.  It leaves young people in the region (220m online) disconnected from global trends and knowledge exchange, and more susceptible to developing extreme views. The demand for English currently outweighs all current supply, which is variable in quality and at country level.

The programme therefore aims to addresses these main problem areas:

  - Many high school leavers don’t have relevant English skills for HE/FE or the workplace

  - Many high school English teachers don’t have the skills to prepare students effectively for work and study

  - There is a lack of comparative data on English levels of school leavers and the classroom practices of their teachers.

  - Lack of digital solutions to support the continuing professional development of English teachers to meet the needs of their learners and lack of digital solutions targeted at the specific needs of school leavers for language learning in an engaging, interactive way with improved learner retention/completion rates.

2.3 	Programme description

The Future English programme aims to equip school leavers across the region with increased English skills to effectively engage in higher education and take up better opportunities in employment. To achieve this, programme will deliver three interconnected strands.

The first one is focused on the clear and comprehensive understanding of the issues that result in school leavers not developing the English proficiency and relevant skills. This problem will be investigated through a comprehensive regional research assessing the English language skills of young people in schools and the teaching practices of their English teachers, as well as other contributing factors such as curriculum, teaching and learning resources and timetabling. The research findings will be shared across the region to support governments to make more informed policy decisions in the area of English teaching in secondary and high schools, as well as to ensure development of appropriate and effective digital solutions which will be able to meet the English language learning needs of young people in the region and the professional development needs of their teachers.

The second strand of the project is focused on engaging English teachers across the region in meaningful continuing professional development by joining communities of practice through a new and innovative platform titled Online Teacher Community (OTC). Teachers will be able to maintain a professional portfolio, share classroom techniques and strategies, engage in collaborative action research projects, join MOOC groups and connect with their peers both within the country and regionally. In addition, this platform will ensure that teachers in remote rural locations and conflict areas can still communicate and collaborate with other teachers through their online teacher communities and can still engage in supported professional development activities.

In the third strand of the project, the UK ELT sector in collaboration with the creative economy and digital sector in the UK and participating countries will create digital learning solutions to enable young people across the region to engage in relevant and exciting self-access English language learning, specifically developing those skills they need for higher education and employment opportunities.

It is within the second strand that support for qualitative research is needed.

3 	Tender Conditions and Contractual Requirements

This section of the RFP sets out the British Council’s contracting requirements, general policy requirements, and the general tender conditions relating to this procurement process (“Procurement Process”).

3.1	Contracting requirements

3.1.1	The contracting authority is the British Council which includes any subsidiary companies and other organisations that control or are controlled by the British Council from time to time (see: http://www.britishcouncil.org/organisation/structure/status).

3.1.2	The appointed supplier will be expected to deliver the goods and/or provide services at the British Council offices in the country of residence and in London UK if required.

3.1.3	The British Council’s contracting and commercial approach in respect of the required goods and/or services is set out at Annex [1] (Terms and Conditions of contract) (“Contract”).  By submitting a tender response, you are agreeing to be bound by the terms of this RFP and the Contract without further negotiation or amendment.

3.1.4	The Contract awarded will be for a duration of 2 months to conclude by 30 April 2022. (To be discussed upon appointment) with an option for an extension.

3.1.5	In the event that you have any concerns or queries in relation to the Contract, you should submit a clarification request in accordance with the provisions of this RFP by the Clarification Deadline (as defined below in the Timescales section of this RFP). Following such clarification requests, the British Council may issue a clarification change to the Contract that will apply to all potential suppliers submitting a tender response.

3.1.6	The British Council is under no obligations to consider any clarifications / amendments to the Contract proposed following the Clarification Deadline, but before the Response Deadline (as defined below in the Timescales section of this RFP). Any proposed amendments received from a potential supplier as part its tender response shall entitle the British Council to reject that tender response and to disqualify that potential supplier from this Procurement Process.

3.2	General Policy Requirements

3.2.1 	By submitting a tender response in connection with this Procurement Process, potential suppliers confirm that they will, and that they shall ensure that any consortium members and/or subcontractors will, comply with all applicable laws, codes of practice, statutory guidance and applicable British Council policies relevant to the goods and/or services being supplied. All relevant British Council policies that suppliers are expected to comply with can be found on the British Council website (https://www.britishcouncil.org/organisation/transparency/policies). The list of relevant policies includes (but it is not limited to): Anti-Fraud and Corruption, Child Protection Policy, Equality, Diversity and Inclusion Policy, Fair Trading, Health and Safety Policy, Environmental Policy, Records Management, and Privacy.

3.3	General tender conditions (“Tender Conditions”)

3.3.1	Application of these Tender Conditions – In participating in this Procurement Process and/or by submitting a tender response it will be implied that you accept and will be bound by all the provisions of this RFP and its Annexes. Accordingly, tender responses should be on the basis of and strictly in accordance with the requirements of this RFP.

3.3.2	Third party verifications – Your tender response is submitted on the basis that you consent to the British Council carrying out all necessary actions to verify the information that you have provided; and the analysis of your tender response being undertaken by one or more third parties commissioned by the British Council for such purposes.

3.3.3 	Information provided to potential suppliers – Information that is supplied to potential suppliers as part of this Procurement Process is supplied in good faith. The information contained in the RFP and the supporting documents and in any related written or oral communication is believed to be correct at the time of issue but the British Council will not accept any liability for its accuracy, adequacy or completeness and no warranty is given as such. This exclusion does not extend to any fraudulent misrepresentation made by or on behalf of the British Council.

3.3.4 	Potential suppliers to make their own enquires – You are responsible for analysing and reviewing all information provided to you as part of this Procurement Process and for forming your own opinions and seeking advice as you consider appropriate. You should notify the British Council promptly of any perceived ambiguity, inconsistency or omission in this RFP and/or any in of its associated documents and/or in any information provided to you as part of this Procurement Process.

3.3.5	Amendments to the RFP – At any time prior to the Response Deadline, the British Council may amend the RFP. Any such amendment shall be issued to all potential suppliers, and if appropriate to ensure potential suppliers have reasonable time in which to take such amendment into account, the Response Deadline shall, at the discretion of the British Council, be extended.

3.3.6 	Compliance of tender response submission – Any goods and/or services offered should be on the basis of and strictly in accordance with the RFP (including, without limitation, any specification of the British Council’s requirements, these Tender Conditions and the Contract) and all other documents and any clarifications or updates issued by the British Council as part of this Procurement Process.

3.3.7	Format of tender response submission – Tender responses must comprise the relevant documents specified by the British Council completed in all areas and in the format as detailed by the British Council in Annex [3] (Supplier Response). Any documents requested by the British Council must be completed in full. It is, therefore, important that you read the RFP carefully before completing and submitting your tender response.

3.3.8	Modifications to tender response documents once submitted – You may modify your tender response prior to the Response Deadline by giving written notice to the British Council. Any modification should be clear and submitted as a complete new tender response in accordance with Annex [3] (Supplier Response) and these Tender Conditions.

3.3.9	Rejection of tender responses or other documents – A tender response or any other document requested by the British Council may be rejected which:

- contains gaps, omissions, misrepresentations, errors, uncompleted sections, or changes to the format of the tender documentation provided;

- contains handwritten amendments which have not been initialled by the authorised signatory;

- does not reflect and confirm full and unconditional compliance with all of the documents issued by the British Council forming part of the RFP;

- contains any caveats or any other statements or assumptions qualifying the tender response that are not capable of evaluation in accordance with the evaluation model or requiring changes to any documents issued by the British Council in any way;

- is not submitted in a manner consistent with the provisions set out in this RFP;

- is received after the Response Deadline.

3.3.10	Disqualification – If you breach these Tender Conditions, if there are any errors, omissions or material adverse changes relating to any information supplied by you at any stage in this Procurement Process, if any other circumstances set out in this RFP, and/or in any supporting documents, entitling the British Council to reject a tender response apply and/or if you or your appointed advisers attempt:

- to inappropriately influence this Procurement Process;

- to fix or set the price for goods or services;

- to enter into an arrangement with any other party that such party shall refrain from submitting a tender response;

- to enter into any arrangement with any other party (other than another party that forms part of your consortium bid or is your proposed sub-contractor) as to the prices submitted; or

- to collude in any other way

- to engage in direct or indirect bribery or canvassing by you or your appointed advisers in relation to this Procurement Process; or

- to obtain information from any of the employees, agents or advisors of the British Council concerning this Procurement Process (other than as set out in these Tender Conditions) or from another potential supplier or another tender response,

the British Council shall be entitled to reject your tender response in full and to disqualify you from this Procurement Process. Subject to the “Liability” Tender Condition below, by participating in this Procurement Process you accept that the British Council shall have no liability to a disqualified potential supplier in these circumstances.

3.3.11	Tender costs – You are responsible for obtaining all information necessary for preparation of your tender response and for all costs and expenses incurred in preparation of the tender response. Subject to the “Liability” Tender Condition below, you accept by your participation in this procurement, including without limitation the submission of a tender response, that you will not be entitled to claim from the British Council any costs, expenses or liabilities that you may incur in tendering for this procurement irrespective of whether or not your tender response is successful.

3.3.12	Rights to cancel or vary this Procurement Process - By issuing this RFP, entering into clarification communications with potential suppliers or by having any other form of communication with potential suppliers, the British Council is not bound in any way to enter into any contractual or other arrangement with you or any other potential supplier. It is intended that the remainder of this Procurement Process will take place in accordance with the provisions of this RFP but the British Council reserves the right to terminate, amend or vary (to include, without limitation, in relation to any timescales or deadlines) this Procurement Process by notice to all potential supplier in writing. Subject to the “Liability” Tender Condition below, the British will have no liability for any losses, costs or expenses caused to you as a result of such termination, amendment or variation.

3.3.13	Consortium Members and sub-contractors – It is your responsibility to ensure that any staff, consortium members, sub-contractors and advisers abide by these Tender Conditions and the requirement of this RFP.

3.3.14	Liability – Nothing in these Tender Conditions is intended to exclude or limit the liability of the British Council in relation to fraud or in other circumstances where the British Council’s liability may not be limited under any applicable law.

4 	Confidentiality and Information Governance

4.1	All information supplied to you by the British Council, including this RFP and all other documents relating to this Procurement Process, either in writing or orally, must be treated in confidence and not disclosed to any third party (save to your professional advisers, consortium members and/or sub-contractors strictly for the purposes only of helping you to participate in this Procurement Process and/or prepare your tender response) unless the information is already in the public domain or is required to be disclosed under any applicable laws.

4.2	You shall not disclose, copy or reproduce any of the information supplied to you as part of this Procurement Process other than for the purposes of preparing and submitting a tender response. There must be no publicity by you regarding the Procurement Process or the future award of any contract unless the British Council has given express written consent to the relevant communication.

4.3	This RFP and its accompanying documents shall remain the property of the British Council and must be returned on demand.

4.4	The British Council reserves the right to disclose all documents relating to this Procurement Process, including without limitation your tender response, to any employee, third party agent, adviser or other third party involved in the procurement in support of, and/or in collaboration with, the British Council. The British Council further reserves the right to publish the Contract once awarded and/or disclose information in connection with supplier performance under the Contract in accordance with any public sector transparency policies (as referred to below). By participating in this Procurement Process, you agree to such disclosure and/or publication by the British Council in accordance with such rights reserved by it under this paragraph.

4.5	The Freedom of Information Act 2000 (“FOIA”), the Environmental Information Regulations 2004 (“EIR”), and public sector transparency policies apply to the British Council (together the “Disclosure Obligations”).

4.6	You should be aware of the British Council’s obligations and responsibilities under the Disclosure Obligations to disclose information held by the British Council. Information provided by you in connection with this Procurement Process, or with any contract that may be awarded as a result of this exercise, may therefore have to be disclosed by the British Council under the Disclosure Obligations, unless the British Council decides that one of the statutory exemptions under the FOIA or the EIR applies.

4.7	If you wish to designate information supplied as part of your tender response or otherwise in connection with this tender exercise as confidential, using any template and/or further guidance provided at Part [2] (Submission Checklist) of Annex [3] (Supplier Response), you must provide clear and specific detail as to:

- the precise elements which are considered confidential and/or commercially sensitive;

- why you consider an exemption under the FOIA or EIR would apply; and

- the estimated length of time during which the exemption will apply.

4.8	The use of blanket protective markings of whole documents such as “commercial in confidence” will not be sufficient. By participating in this Procurement Process you agree that the British Council should not and will not be bound by any such markings.

4.9	In addition, marking any material as “confidential” or “commercially sensitive” or equivalent should not be taken to mean that the British Council accepts any duty of confidentiality by virtue of such marking. You accept that the decision as to which information will be disclosed is reserved to the British Council, notwithstanding any consultation with you or any designation of information as confidential or commercially sensitive or equivalent you may have made. You agree, by participating further in this Procurement Process and/or submitting your tender response, that all information is provided to the British Council on the basis that it may be disclosed under the Disclosure Obligations if the British Council considers that it is required to do so and/or may be used by the British Council in accordance with the provisions provision of this RFP.

4.10	Tender responses are also submitted on the condition that the appointed supplier will only process personal data (as may be defined under any relevant data protection laws) that it gains access to in performance of this Contract in accordance with the British Council ’s instructions and will not use such personal data for any other purpose. The contracted supplier will undertake to process any personal data on the British Council’s behalf in accordance with the relevant provisions of any relevant data protection laws and to ensure all consents required under such laws are obtained.

5	Tender Validity

5.1	Your tender response must remain open for acceptance by the British Council for a period of up to 60 days from the Response Deadline. A tender response not valid for this period may be rejected by the British Council.

6	Payment and Invoicing

6.1 	The British Council will pay correctly addressed and undisputed invoices within 30 days in accordance with the requirements of the Contract. Suppliers to the British Council must ensure comparable payment provisions apply to the payment of their sub-contractors and the sub-contractors of their sub-contractors. General requirements for an invoice for the British Council include:

- A description of the good/services supplied is included.

- The British Council Purchase Order number is included.

- It is sent electronically via email in PDF format to BC.Invoices@britishcouncil.org or by post to:

The British Council, Corporate Services – Bridgewater House, 58 Whitworth Street, Manchester, M1 6BB

- Specification

  - Scope

The Online Teachers Community (OTC) is teacher-driven and teacher-centred professional development platform for teachers of English from Armenia, Azerbaijan, Georgia, Kazakhstan, Ukraine and Uzbekistan. It is an online programme that includes self-access learning modules, as well as a space for teachers’ interaction and peer learning through live sessions, forums and webinars. Learning modules are based on Teaching for Success, the British Council’s Continuing Professional Development framework. For each of the participating country learning modules are designed based on teachers’ needs and in agreement with Ministry of Education. As presented in the table, number of modules, duration of the programme and number of teachers included vary from country to country.

| Core learning modules |
| --- |
| Country | Number of teachers per cohort (planned) | Number of teachers’ cohorts (planned) | Number of modules per cohort | Duration of each cohort |
| Armenia | 1,000 | 2 cohorts | 3 modules | 10 weeks |
| Azerbaijan | 2,000 | 2 cohorts | 5 modules | 11 weeks |
| Georgia | 2,000 | 1 cohort | 5 modules | 5 months |
| Kazakhstan | 2,000 | 2 cohorts | 5 modules | 10 weeks |
| Ukraine | 1,000 | 3 cohorts | 6 modules | 6 weeks |
| Uzbekistan | 1,000 | 2 cohorts | 5 modules | 10 weeks |

In addition to the core cohorts and learning modules in each country, there are additional thematic courses delivered throughout the programme. These courses include Mentors training for Ukrainian teachers as well as Action Research course and Assessment Literacy course, both open for teachers from all participating countries.

| Thematic courses |
| --- |
| Course | Open to teacher from countries | Number of courses | Duration of the course | Number of teachers involved |
| Mentor training | Ukraine | 1 | 5 weeks | 300 |
| Exploratory Action Research (pilot) | All participating countries | 1 | 12 weeks | 25 |
| Assessment Literacy for ELTs | All participating counties | 7 | 7 weeks | ~1,500 |

Throughout the implementation of the programme, British Council programme team collects quantitative data from teachers across all countries. This includes (1) data on teachers’ demography (collected early in the process); (2) teachers’ feedback and perspective on the programme delivery and experience with different learning elements (collected mid-way through the programme); and (3) teachers’ feedback on knowledge, skills and practices gained through the programme (collected at the end). There is also a plan to do a follow-up survey with teachers that participated in the programme to explore to what extent they applied/ gained knowledge and skills in the classroom. Follow-up survey will be administrated in May/June 2022 but is subject to further approval.

Fully aware of the limitations of quantitative data alone, British Council is interested in expanding evidence base and strengthening it through additional qualitative evidence. Guided by this idea, British Council is looking for the consultancy to collect qualitative data across countries and cohorts from teachers that participated in the programme. As a general approach, it is expected that small group of teachers from each country and cohort/course will be included in the qualitative data collection. Data will be collected at the end of the cohort which will allow teachers’ overall reflection on the learning process and its benefits. All data collection will be done online.

The whole assignment needs to be completed by the end of March 2022.

British Council programme team will provide all needed logistics and support the process.

7.2 Purpose

The purpose of this assignment is to strengthen evidence on the implementation and achievements of the professional development programme and community of practice delivered through the Online Teachers Community platform. Within this purpose, it is expected form the consultancy to conduct formative qualitative research and collect qualitative evidence on teachers’ experience, perspectives and benefits gained through the OTC platform. Research findings will be primarily used to support further improvement of the programme.

It is expected from the selected consultancy to design the qualitative methodology and collect qualitative data from teachers who participated in the professional development programme and community of practice on the OTC platform. The assignment should be focused on following themes/questions:

- Learning experience - questions about the overall programme experience. Possible areas to explore are: which segments of the programme work, which don’t work so well; how relevant is the programme, how useful it is; what can be improved, etc.

- Community of practice – questions about peer learning and support. For the British Council, establishing the community of practice, providing space for teachers’ peer learning/support and encouraging it, is an important aspect of the programme. Possible areas to explore are if teachers feel like being part of the community; if they connected with and learnt from their peers.

- Benefits and takeaways – questions about key benefits and takeaways from the programme. Possible areas to explore are: what are key learnings/takeaways from the programme; have the programme influenced teachers’ practice, what changed; how likely it is that changes in practices will sustain after the project.

7.3 Methodology

As mentioned above, British Council programme team is collecting quantitative data, so this assignment is exclusively focused on qualitative data collection. Having in mind differences between countries in terms of context, needs and learning modules, it is expected that data collection will include small group of teachers from each country and cohort/course. Sampling strategy and size will be agreed between consultancy and British Council programme team.

Regarding data collection, we foreseen that data will be collected through Focus Group Discussions (e.g. one FGD per cohort per country) as the efficient way to engage more teachers. However, we are open for suggestions on other ways of data collection.

It is expected that data collection and analysis will follow themes/questions proposed above and provide evidence-based insight on teachers’ experience, perspectives and benefits.

  - It is expected the consultant will meet the following deliverables:

- Producing Inception Report including detailed research plan – Inception report should provide brief understanding of the programme and elaborate in details on the research plan which should include: (i) research approach, design and methodology; (ii) data collection methods, tools and instruments; (iii) data analysis approach; (iii) risks and limitations; and (iv) timelines. Purpose of the inception report is to ensure mutual agreement on the approach and expectations from the process.

- Qualitative data collection – Once Inception report is agreed and approved, consultant should work on the operationalisation of the plan. All data collection will be done online.

- Report – Report should include (minimum, but not limited to): executive summary, description of intervention, purpose and methodology applied, findings, conclusions, recommendations and lessons learnt, annexes. Report should provide objective and evidence-based findings and actionable recommendations that can strengthen the programme, support decision-making and organizational learning and accountability.

7.4	Research Partner Specification

- An institution or individual consultant with proven track record and expertise in carrying out qualitative research/evaluation both face-to-face and online

- Expertise in education projects. Preferably expertise in English language teaching (ELT) and teachers’ professional development.

- Understanding of the local education context and/or previous experience of working in post-soviet countries

- Ability to work as part of a remote team

Bidders should explain the extent to which they expect to use national or local consultants in the evaluation. In general, it is assumed that in-country work would either be done by programme staff or by in-country consultants.

Bidders should outline how they will handle logistical matters including issues such as duty of care, safeguarding etc. In general, it is expected that the evaluators will be self- reliant in terms of logistics.

Bidders should explain how they will ensure the ethics of the work they do.

7.5	Form of proposal

Please submit your proposal to Addeh Hovassapian by email addeh.hovassapian@britishcouncil.am  Your proposal should be a maximum of 5 pages of A4, by excluding the supplier response document (see Annex 3).

Provide details of how you will ensure quality control.

Give details of full cost, including a break-down of cost per phase / deliverable and the hourly rates and anticipated number of hours involved in conducting the project.

8 	Mandatory Requirements / Constraints

8.1	As part of your tender response, you must confirm that you meet the mandatory requirements / constraints, if any, as set out in the British Council’s specification forming part of this RFP. A failure to comply with one or more mandatory requirements or constraints shall entitle the British Council to reject a tender response in full.

9 	Qualification Requirements

9.1	As part of your tender response, you must confirm compliance with any qualification requirements as set out at Annex [2] (Qualification Questionnaire). A failure to comply with one or more such qualification requirements shall entitle the British Council to reject a tender response in full.

10	Key background documents and further information

10.1	Further relevant background documents / information may be provided to potential suppliers as set out below, as an Annex to this RFP and/or by way of the issue of additional documents / links to additional information / documents. Where no such information / documents are provided, this Section of the RFP will not apply.

10.2	The following additional documentation / information is provided as part of this RFP

- Future English: External Programme Brief/Questions and Answers

- British Council Ethics Policy, available upon request

11	Timescales

11.1 	Subject to any changes notified to potential suppliers by the British Council in accordance with the Tender Conditions, the following timescales shall apply to this Procurement Process:

The table below outlines the M&E deliverables to be provided by the consultancy and the anticipated timeline for them.  The bidders are welcome to comment on them.

Please note the following:

- most data collection would be done by British Council staff members (based on tools and data collection plans developed as part of this consultancy and in consultation with the British Council);

- the British Council will own all data collated.

| No | Deliverable | Time |
| --- | --- | --- |
| 1 | Study the project documentation, develop research plan and write an inception report | End of February 2022 |
| 2 | Qualitative data collection with teachers | March 2022 |
| 3 | Data analysis and development of the Report | April 2022 |

11.2 	The indicative budget for the evaluation is up to a maximum of £15,000 inclusive of VAT.

12 	Instructions for Responding

12.1	The documents that must be submitted to form your tender response are listed at Part [2] (Submission Checklist) of Annex [3] (Supplier Response) to this RFP. All documents required as part of your tender response should be submitted to Addeh Hovassapian by email addeh.hovassapian@britishcouncil.am by the Response Deadline, as set out in the Timescales section of this RFP.

12.2 	The following requirements should be complied with when summiting your response to this RFP:

- Please ensure that you send your submission in good time to prevent issues with technology – late tender responses may be rejected by the British Council.

- Do not submit any additional supporting documentation with your RFP response except where specifically requested to do so as part of this RFP. PDF, JPG, PPT, Word and Excel formats can be used for any additional supporting documentation (other formats should not be used without the prior written approval of the British Council).

- All attachments/supporting documentation should be provided separately to your main tender response and clearly labelled to make it clear as to which part of your tender response it relates.

- If you submit a generic policy / document, you must indicate the page and paragraph reference that is relevant to a particular part of your tender response.

- Unless otherwise stated as part of this RFP or its Annexes, all tender responses should be in the format of the relevant British Council requirement with your response to that requirement inserted underneath.

- Where supporting evidence is requested as ‘or equivalent’ you must demonstrate such equivalence as part of your tender response.

- Any deliberate alteration of a British Council requirement as part of your tender response will invalidate your tender response to that requirement and for evaluation purposes you shall be deemed not to have responded to that particular requirement.

- Responses should concise, unambiguous, and should directly address the requirement stated.

- Your tender responses to the tender requirements and pricing will be incorporated into the Contract, as appropriate.

13 	Clarification Requests

13.1	All clarification requests should be submitted to Addeh Hovassapian by email addeh.hovassapian@britishcouncil.am  by the 8 February 2022. The British Council is under no obligation to respond to clarification requests received after the Clarification Deadline.

13.2	Any clarification requests should clearly reference the appropriate paragraph in the RFP documentation and, to the extent possible, should be aggregated rather than sent individually.

13.3	The British Council reserves the right to issue any clarification request made by you, and the response, to all potential suppliers unless you expressly require it to be kept confidential at the time the request is made. If the British Council considers the contents of the request not to be confidential, it will inform you and you will have the opportunity to withdraw the clarification query prior to the British Council responding to all potential suppliers.

13.4	The British Council may at any time request further information from potential suppliers to verify or clarify any aspects of their tender response or other information they may have provided. Should you not provide supplementary information or clarifications to the British Council by any deadline notified to you, your tender response may be rejected in full and you may be disqualified from this Procurement Process.

14 	Evaluation Criteria

14.1	You will have your tender response evaluated as set out below:

Stage 1:  Tender responses will be checked to ensure that they have been completed correctly and all necessary information has been provided.  Tenders’ responses correctly completed with all relevant information being provided will proceed to Stage 2.  Any tender responses not correctly completed in accordance with the requirements of this RFP and/or containing omissions may be rejected at this point.  Where a tender response is rejected at this point it will automatically be disqualified and will not be further evaluated.

↓

Stage 2:  The completed Qualification Questionnaire (if used) will then be reviewed to confirm that the potential supplier meets all of the qualification criteria set out in the questionnaire. Potential suppliers that meet the qualification criteria will proceed to Stage 3.  Potential suppliers that do not meet the qualification criteria set out in the Qualification Questionnaire (if used) may be excluded from the Procurement Process at this point. Where a potential supplier is excluded at this point, its tender response will be rejected in full and not evaluated further and the supplier will automatically be disqualified from this Procurement Process.

↓

Stage 3:  If a bidder succeeds in passing Stages 1 and 2 of the evaluation, then it will have its detailed tender response to the British Council’s requirements evaluated in accordance with the evaluation methodology set out below. Information provided as part of Qualification Questionnaire (if used) responses may also be verified as part of this stage.

14.2	Responses from potential suppliers will be assessed to determine the most economically advantages tender using the following criteria and weightings and will be assessed entirely on your response submitted:

| Criteria | Weighting |
| --- | --- |
| Technical/Relevant qualifications | 25% |
| Interpretation of TOR – approach, methods etc. | 25% |
| Relevant experience in working on large-scale English language training projects | 25% |
| Financial | 25% |

14.3	Consultancy details

Deadline for submission of the proposal: 10 February 2022, 23.59h GMT

Dates of the consultancy: a specific timeframe would be discussed with the successful candidate / institution and would cover the duration of the overall programme. The start date of the consultancy would be 20 February 2022.

Selection procedure:

All submitted proposals will be reviewed and shortlisted by British Council representatives. The three top proposals will be selected for consideration and experts will be contacted by 15 February 2022 for more information on details of the proposal, if needed.

The final decision will be made and announced no later than 17 February 2022.

14.4	Scoring Model – Tender responses will be subject to an initial review at the start of Stage 3 of the evaluation process. Any tender responses not meeting mandatory requirements or constraints (if any) will be rejected in full at this point and will not be assessed or scored further.  Tender responses not so rejected will be scored by an evaluation panel appointed by the British Council for all criteria other than Commercial using the following scoring model:

| Points | Interpretation |
| --- | --- |
| 10 | Excellent – Overall the response demonstrates that the bidder meets all areas of the requirement and provides all of the areas evidence requested in the level of detail requested. This, therefore, is a detailed excellent response that meets all aspects of the requirement leaving no ambiguity as to whether the bidder can meet the requirement. |
| 7 | Good – Overall the response demonstrates that the bidder meets all areas of the requirement and provides all of the areas of evidence requested but contains some trivial omissions in relation to the level of detail requested in terms of either the response or the evidence. This, therefore, is a good response that meets all aspects of the requirement with only a trivial level ambiguity due the bidder’s failure to provide all information at the level of detail requested. |
| 5 | Adequate – Overall the response demonstrates that the bidder meets all areas of the requirement, but not all of the areas of evidence requested have been provided. This, therefore, is an adequate response, but with some limited ambiguity as to whether the bidder can meet the requirement due to the bidder’s failure to provide all the evidence requested. |
| 3 | Poor – The response does not demonstrate that the bidder meets the requirement in one or more areas. This, therefore, is a poor response with significant ambiguity as to whether the bidder can meet the requirement due to the failure by the bidder to show that it meets one or more areas of the requirement. |
| 0 | Unacceptable – The response is non-compliant with the requirements of the RFP and/or no response has been provided. |

14.5	Commercial Evaluation – Your “Overall Price” (as calculated in accordance with requirements of Annex [4] (Pricing Approach) for the goods and/or services will be evaluated by the evaluation panel for the purposes of the commercial evaluation. Prices must not be subject to any pricing assumptions, qualifications or indexation not provided for explicitly by the British Council as part of the pricing approach. In the event that any prices are expressed as being subject to any pricing assumptions, qualifications or indexation not provided for by the British Council as part of the pricing approach, the British Council may reject the full tender response at this point. The British Council may also reject any tender response where the Overall Price for the goods and/or services is considered by the British Council to be abnormally low following the relevant processes set out under the EU procurement rules.  A maximum offer score of 10 will be awarded to the tender response offering the lowest “Overall Price”. Other tender responses will be awarded a mark by application of the following formula: (Lowest Overall Price/Overall Price being evaluated) x 10 (rounded to two decimal places) = commercial score.

14.6	Moderation and application of weightings – The evaluation panel appointed for this procurement will meet to agree and moderate scores for each award criteria. Final scores in terms of a percentage of the overall tender score will be obtained by applying the relevant weighting factors set out as part of the award criteria table above. The percentage scores for each award criteria will be amalgamated to give a percentage score out of 100.

14.7	The winning tender response – The winning tender response shall be the tender response scoring the highest percentage score out of 100 when applying the above evaluation methodology, which is also supported by any required verification evidence (to include, without limitation, any updated information or references relating to any Qualification Question responses) obtained by the Authority relating to any self-certification or other requirements referred to in the Qualification Questionnaire (if used). If any verification evidence requested from a supplier, or a relevant third party as may be referred to by the supplier in the Qualification Questionnaire (if used) as a party prepared to provide such information, is not provided in accordance with any timescales specified by the British Council and/or any evidence reviewed by the British Council (whose decision shall be final) does not demonstrate compliance with any such requirement, the British Council may reject that tender response in full and disqualify the potential winning supplier from the Procurement Process at that point.

List of Annexes forming part of this RFP (issued as separate documents):

Annex 1 - Terms and Conditions of Contract

Annex 2 – Qualification Questionnaire

Annex 3 – Supplier Response

Annex 4 – Pricing Approach

Future English: External Programme Brief/Questions and Answers

What problem is this programme addressing?

The objective of this programme is to address the reported and perceived problem of low English language skills experienced by school leavers who are entering the world of work or higher education.

Through carrying out research to gather up-to-date and useful insights, we can develop solutions to help with this issue, as well as supporting the professional development of English teachers to help support learners.

Why is the British Council doing this?

We want to create opportunities for young people to develop the English language skills they need to succeed in education and work.

We believe young people have a role to play in their communities, countries and globally. The British Council’s ‘English Effect’ research shows a command of English not only enhances an individual’s economic prospects, but also contributes to national growth and competitiveness. Beside employment opportunities, English is becoming increasingly important for further and higher education, and for accessing courses in other countries and also self-access digital courses.

We want to support: 
Young people - especially those based in remote / rural / edge of conflict zones. Girls, in particular, have limited access to skills and learning opportunities (FCO Girls’ Education 2018), and this, together with other barriers in society, continues to limit the future employability and their capability to influence or to engage with the development of their communities and peacebuilding.

English teachers - often they are poorly trained and sometimes use outdated methodologies, with little access to continuing their professional development.

Schools - they often lack support and study materials (including multimedia) which does not aid learning.

The combination of the above means that students have limited chances for better careers and better lives. We want to help transform this situation using our expertise in education to help young people create a better future.

What countries will Future English run in?

Armenia, Azerbaijan, Georgia, Kazakhstan, Ukraine and Uzbekistan.

Why are we focusing on these countries?

In these countries, we have issues in terms of low English language skills when it comes to school leavers. We also know that teachers would be responsive to continuous professional development as they don’t always have easy access and the tools to support learners in this area. We also know that in the majority of these countries, education reforms are currently underway so there’s a real opportunity for us to support and play a positive role.

Who are the main beneficiaries of this programme?

English language teachers, and through them, ultimately young people.

# Footnotes

Pilot cohort, plus one cohort per each country